## Sheet1
|  |  | Dates | Monday, 2 March 2020 | Monday, 9 March 2020 | Monday, 15 March 2020 | Monday, 23 March 202 | Monday, 30 March 2020 | Monday, 6 April 2020 | Monday, 13 April 2020 | Monday, 20 april 2020
NR | Task | Hours | Weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
1 | Research Content, write 'Epic' 'User Story' | 112.5 |  | 1
2 | Write Content and decide on materia | 150 |  | 2 | 2
3 | Build the page in HTML / CSS Javascript | 300 |  |  |  | 3 | 3 | 3
4 | Test the site with real users | 37.5 | [6 empty] | 4
5 | Fix bugs and go over any issues | 75 | [6 empty] | 5 | 5
6 | Rollout the project | 75 | [7 empty] | 6 | 6
1 | Research Content | 75 |  | 1
2 | Photographs / Content | 37.5 |  | 2 | 2
3 | Ux-Design Mockup | 75 |  |  |  | 3 | 3
4 | Stakeholder Meeting's | 37.5 |  |  |  |  | 4 |  |  | 4
5 | Incorporation of Ux-Design with content | 37.5 |  |  |  |  | 5 | 5
6 | Build Back-End of the site | 112.5 | [5 empty] | 6 | 6
NR | Team Members | Title | [9 empty] | Total Hours
1 | Alexander Hardeland | Project Manager |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 300
2 | Helge Grønstad | Photographer / UX |  | 2 | 2 | 2 | [5 empty] | 112.5
3 | Mia Sørhus | Ux / Front-End |  |  |  | 3 | 3 | 3 |  |  |  | 113.5
4 | Bjørnar Grindheim | Content / Copywriter |  | 4 | 4 |  |  |  |  | 4 |  | 114.5
5 | Stian Hansen | Full Stack | [5 empty] | 5 | 5 |  | 5 | 115.5
Project in total Hours: 750